## Sheet1
PSP Time Recording Log
Student | Tom Son
Program | Number Guessing game
Instructor | Amit / Luofeng
Project | Phase | Date | Start | Int Time | Stop | Delta Time | Comments
Create a guessing game | Planning | 2019-03-19 | 21:35 |  | 22:15 |  | Creating Requirements Statement, Task Summary and Time Log
| Designing | 2019-03-25 | 22:09 |  | 22:47 |  | Drawing a design level class diagram & Activity diagram
| Coding | 2019-03-25 | 22:50 |  | 23:08 |  | Starting code based on design
| Coding | 2019-03-29 | 23:34 |  | 12:13 |  | Continue on coding
| Coding | 2019-03-30 | 0:33 |  | 1:09 |  | Continue on coding
| Testing | 2019-03-30 | 14:59 |  | 15:24 |  | Starting test for code
| Testing | 2019-03-30 | 16:03 |  | 16:32 |  | Found some issues and the way to fix
| Coding | 2019-04-01 | 16:53 |  | 17:54 |  | Fixing code and try to separate classes, Controller & Model

## Instructions
Time Recording Log Instructions
General | - Record all of the time you spend on the project.
- Record the time in minutes.
- Be as accurate as possible.
- If you need additional space, use another copy of the form.
- If you forget to record the starting, stopping, or interruption time for an activity, promptly enter your best estimate.
Header | - Enter your name and the date.
- Enter the program name and number.
- Enter the instructor’s name and the programming language you are using.
Project | Enter the program name or number.
Phase | Enter the name of the phase for the activity you worked on, e.g. Planning, Design, Test.
Start Date and Time | Enter the date and time when you start working on a process activity.
Interruption Time | - Record any interruption time that was not spent on the process activity.
- If you have several interruptions, enter their total time.
- You may enter the reason for the interrupt in comments.
Stop Date and Time | Enter the date and time when you stop working on that process activity.
Delta Time | Enter the clock time you actually spent working on the process activity, less the interruption time.
Comments | Enter any other pertinent comments that might later remind you of any unusual circumstances regarding this activity.